## Sheet1
Week | Task | Phase | Duration (Days) | Status
Week 1 | Project Planning & Topic Approval | Planning | 5 | Done
Week 2 | Requirement Gathering | Phase 1 | 7 | Done
Week 3 | Figma Prototype (UI Design) | Phase 2 | 7 | Done
Week 4 | ERD & Schema Design | Phase 3 | 7 | In Progress
Week 5-8 | Flutter App Development + Database Integration | Development | 28 | Pending
Week 9 | Testing (Unit & UI Tests) | Testing | 7 | Pending
Week 10 | Bug Fixes & Refinement | Testing | 7 | Pending
Week 11 | Deployment Preparation | Deployment | 7 | Pending
Week 12 | Final Report & Submission | Documentation | 7 | Pending